## Sheet1
Name | Process | Progress | Dev Assigned | Remarks
Login Citrix | 1.1-1.2 | Done | Ishmeet
WellCare Inventory Portal Login | 1.3- | Not Assigned
Inventory Download | 1.4-1.8 , 2.1 | Done | Vinay
Xcelys Login + Claim Loading | 2.2-2.6 | Done | Ishmeet
Fetching Hold Code | 2.7-2.9 | In Progress | Ishmeet
CMI Tool Navigation | Not in document | Done | Gurleen
XML Parsing | Not in document | Done | Vinay and Pnakaj
Getting Potential Claim Number | 2.10 - 2.14 | In Progress | Gurleen | Check if potential duplicate claim numbers are being fetched or not
9 parameter Comparision | 2.15- | In Progress | Harnoor
Claim Submission Reason code processing | 2.16- | Not Assigned |  | Dependency - Claim Submission Reason Code - OCR may be req
Logical Comparision | 2.17- | Done | Vibhor
Logical Comparision | 2.18- | Done | Harnoor | Tin Exctraction done in XML Parsing
Logical Comparision | 2.19- | Done | Vibhor
Logical Comparision | 2.20- 2.21 | Done | Harnoor
Claim Payment | 3.0 - | Not Done |  | Environment Issue
Claim Denied | 4.0- | Not Done |  | Environment Issue